## Project Plan
Phase | Week | Goal | Deliverables | Status
Phase 1: Core Security Infrastructure & Compliance | Week 1-2 | Establish Zero Trust security principles | Never trust, always verify; Multi-tenant security boundaries; Tenant-specific AES-256-GCM; HSM integration; Nigerian data localization | Completed
Phase 1: Core Security Infrastructure & Compliance | Week 3-4 | Implement AI-powered fraud detection with ML models | Fraud-service implementation; TensorFlow.js integration; Risk scoring API <500ms; Biometric analysis; VPN/proxy/Tor detection | Completed
Phase 1: Core Security Infrastructure & Compliance | Week 5-6 | Implement security-first request processing | Multi-tenant AI base; WAF with OWASP Top 10; Rate limiting; AI middleware; Audit logging | Completed
Phase 1: Core Security Infrastructure & Compliance | Week 7-8 | Implement Central Bank of Nigeria regulatory requirements | CBN compliance; Incident reporting; Data localization verification; Security audit prep; Business continuity plans | Completed
Phase 1: Core Security Infrastructure & Compliance | Week 9-10 | Start PCI DSS compliance and security monitoring | Network segmentation; PCI DSS framework; SIEM setup; Real-time monitoring; Audit trails & forensics
Phase 2: AI Intelligence Services | Week 11-13 | Implement natural language banking assistant | AI intelligence service; OpenAI banking integration; Intent classification; Entity extraction; Multi-language support
Phase 2: AI Intelligence Services | Week 14-16 | Voice-enabled banking operations | Voice processing pipeline; Speech-to-text; NLP commands; Voice authentication; Cross-platform UI
Phase 2: AI Intelligence Services | Week 17-18 | Complete AI feature integration | Suggestions engine; Business intelligence; User insights; Optimization; Testing
Phase 3: Enhanced Database & Analytics | Week 19-20 | Implement AI data management | Enhanced DB schema; AI logs; Fraud analytics; Behavior storage; Privacy compliance
Phase 3: Enhanced Database & Analytics | Week 21-22 | AI analytics and performance monitoring | AI metrics; Fraud analytics dashboard; Conversation analytics; BI reporting; Model tracking
Phase 4: Advanced Frontend Features | Week 23-25 | Implement AI-powered user interface | AI chat; Voice interface; Smart suggestions; Fraud alerts; Multi-language UI
Phase 4: Advanced Frontend Features | Week 26-27 | Security-focused user experience and admin interface | Biometric auth UI; MFA UI; Security dashboard; Admin Panel; Risk indicators; Fraud notifications; User management
Phase 5: Integration & Production | Week 28-29 | Complete system integration | End-to-end integration; Optimization; Testing suite; Penetration testing; Load testing
Phase 5: Integration & Production | Week 30 | Production deployment preparation and alerting | Production config; Real-time alerts; Monitoring; Escalation workflows; Incident response; Documentation; Audit compliance; Go-live