## OrokiiPay_Project_Dashboard
OROKIIPAY MULTI-TENANT BANKING PLATFORM - PROJECT DASHBOARD
PROJECT OVERVIEW
Metric | Value | Target | Status
Total Tasks | 109 | 109 | On Track
Completed Tasks | 14 | 14 | 100%
In Progress Tasks | 0 | 95 | Not Started
Overall Completion | 12.8% | 100% | 58% (with backend weight)
Estimated Completion Week | Week 34 | Week 34 | On Schedule
Current Phase | Phase 1 | Phase 3D | Planning
PHASE COMPLETION STATUS
Phase | Total Tasks | Completed | In Progress | Not Started | % Complete | Timeline
Completed Work | 14 | 14 | 0 | 0 | 100% | Weeks 1-10
Phase 1 - Platform Administration | 15 | 0 | 0 | 15 | 0% | Weeks 11-16
Phase 2A - Transaction Reversals | 8 | 0 | 0 | 8 | 0% | Weeks 17-20
Phase 2B - NIBSS Production | 7 | 0 | 0 | 7 | 0% | Weeks 17-23
Phase 2C - Savings Products | 10 | 0 | 0 | 10 | 0% | Weeks 17-23
Phase 2D - Loan Products | 11 | 0 | 0 | 11 | 0% | Weeks 21-27
Phase 3A - Enhanced Transfers | 6 | 0 | 0 | 6 | 0% | Weeks 23-26
Phase 3B - Account Management | 5 | 0 | 0 | 5 | 0% | Weeks 24-27
Phase 3C - Bill Payments | 5 | 0 | 0 | 5 | 0% | Weeks 27-29
Phase 3D - Advanced Features | 5 | 0 | 0 | 5 | 0% | Weeks 27-31
Security Enhancements | 7 | 0 | 0 | 7 | 0% | Weeks 20-29
Third-Party Integrations | 3 | 0 | 0 | 3 | 0% | Weeks 29-34
Optimization | 5 | 0 | 0 | 5 | 0% | Weeks 26-30
Documentation | 4 | 0 | 0 | 4 | 0% | Weeks 28-32
PRIORITY BREAKDOWN
Priority Level | Task Count | Completed | Outstanding | % of Total
Critical | 43 | 8 | 35 | 39.4%
High | 39 | 5 | 34 | 35.8%
Medium | 23 | 1 | 22 | 21.1%
Low | 4 | 0 | 4 | 3.7%
COMPONENT COMPLETION STATUS
Component | % Complete | Status | Notes
Backend Infrastructure | 87% | Mostly Complete | Core APIs functional
Frontend Screens | 35% | In Progress | 8 of 27 screens done
Design System | 100% | Complete | Production ready
Testing Framework | 100% | Complete | Production ready
AI System | 100% | Complete | Production ready
Cloud Deployment | 100% | Complete | Production ready
Platform Admin | 0% | Not Started | Highest priority
Revenue Features (Savings/Loans) | 10% | Not Started | High business value
Security (Production) | 40% | Partial | Needs enhancement
Multi-Language | 100% | Complete | 4 languages supported
Multi-Currency | 100% | Complete | 6 currencies supported
TEAM WORKLOAD ALLOCATION
Team | Assigned Tasks | % of Total Work | Critical Path | Notes
Backend Team | 45 | 41.3% | Yes | Platform admin APIs + NIBSS + Savings/Loans
Frontend Team | 35 | 32.1% | Yes | 19 screens outstanding
Security Team | 7 | 6.4% | Yes | Production security critical
AI Team | 3 | 2.8% | No | Fraud detection + credit scoring
DevOps Team | 3 | 2.8% | No | Infrastructure optimization
QA Team | 8 | 7.3% | Yes | Testing for all new features
Compliance Team | 1 | 0.9% | Yes | CBN compliance
Business Team | 1 | 0.9% | No | NIBSS credentials
Product Team | 3 | 2.8% | No | Documentation
Design Team | 0 | 0% | No | Design system complete
RISK ASSESSMENT
Risk Category | Risk Level | Mitigation Status | Impact
NIBSS Production Credentials | High | Pending | Delays Phase 2B
Credit Bureau Integration | Medium | Pending | Delays Phase 2D
Platform Admin Complexity | High | Planning Complete | Schedule risk
Frontend Screen Conversion | Medium | Well Defined | Resource risk
Security Compliance | High | Framework Ready | Regulatory risk
Team Capacity | Medium | Manageable | Schedule risk
Third-Party Dependencies | Medium | Identified | Feature risk
MILESTONE TIMELINE
Milestone | Target Week | Status | Dependencies
Platform Admin Complete | Week 16 | Not Started | Phase 1 tasks
Transaction Reversals Live | Week 20 | Not Started | Phase 2A tasks
NIBSS Production Integration | Week 23 | Not Started | NIBSS credentials
Savings Products Live | Week 23 | Not Started | Phase 2C tasks
Loan Products Live | Week 27 | Not Started | Credit bureau + Phase 2D
Enhanced Transfers Complete | Week 26 | Not Started | Phase 3A tasks
Bill Payments Live | Week 29 | Not Started | Biller integrations
Security Hardening Complete | Week 29 | Not Started | Security tasks
Performance Optimization | Week 30 | Not Started | Optimization tasks
Full Platform Launch | Week 34 | Not Started | All phases complete
REVENUE IMPACT FEATURES
Feature | Priority | Business Value | Completion % | Target Week | Revenue Impact
Savings Products | Critical | Very High | 0% | Week 23 | High - Interest margin
Loan Products | Critical | Highest | 0% | Week 27 | Highest - Loan interest
Transaction Reversals | Critical | High | 0% | Week 20 | Medium - Compliance + service
NIBSS Integration | Critical | High | 10% | Week 23 | High - Interbank fees
Bill Payments | High | Medium | 0% | Week 29 | Medium - Transaction fees
Platform Admin | Critical | Very High | 0% | Week 16 | Critical - Multi-tenant revenue
Enhanced Transfers | High | Medium | 0% | Week 26 | Low - Improved UX
OUTSTANDING WORK BY CATEGORY
Category | Tasks | Weeks Required | Priority Level | Team Dependencies
Platform Administration | 15 | 6 weeks | Critical | Backend + Frontend + Security
Revenue Features | 29 | 11 weeks | Critical | Backend + Frontend + AI
Core Banking Features | 16 | 7 weeks | High | Backend + Frontend
Security Hardening | 7 | 9 weeks | Critical | Security + DevOps
Third-Party Integrations | 3 | 6 weeks | Medium | Backend
Optimization | 5 | 5 weeks | High | Backend + DevOps + QA
Documentation | 4 | 5 weeks | Low | Product
WEEKLY RESOURCE REQUIREMENTS
Week Range | Backend FTE | Frontend FTE | Security FTE | QA FTE | Total FTE | Focus Area
Weeks 11-16 | 2 | 2 | 1 | 0.5 | 5.5 | Platform Administration
Weeks 17-20 | 3 | 2 | 0.5 | 1 | 6.5 | Reversals + NIBSS + Savings
Weeks 21-27 | 3 | 3 | 1 | 1 | 8 | Loans + Savings + Transfers
Weeks 28-31 | 2 | 2 | 1 | 1 | 6 | Bill Payments + Advanced Features
Weeks 32-34 | 1 | 1 | 0.5 | 1 | 3.5 | Optimization + Documentation
KEY DEPENDENCIES
Dependency Type | Dependent Tasks | Blocking Item | Risk Level | Mitigation
External - NIBSS | 7 tasks | NIBSS credentials | High | Engage business team now
External - Credit Bureau | 4 tasks | CRC integration | Medium | Start negotiations early
Internal - Platform Admin | All Phase 2-3 tasks | JWT + subdomain routing | Critical | Complete Phase 1 first
Internal - Database Schema | All feature tasks | Migration testing | Medium | Rigorous testing
Internal - Team Capacity | All tasks | Resource availability | Medium | Prioritize critical path
ESTIMATED PROJECT COSTS (Person-Weeks)
Phase | Backend | Frontend | Security | AI | QA | DevOps | Product | Total PW | Cost Estimate
Completed | 48 | 24 | 8 | 12 | 9 | 6 | 3 | 110 | 220000
Phase 1 | 8 | 8 | 2 | 0 | 1 | 0 | 0 | 19 | 38000
Phase 2 (All) | 24 | 16 | 1 | 6 | 4 | 0 | 0 | 51 | 102000
Phase 3 (All) | 12 | 12 | 0 | 0 | 3 | 0 | 0 | 27 | 54000
Security | 0 | 0 | 12 | 2 | 2 | 3 | 0 | 19 | 38000
Integration | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 12000
Optimization | 4 | 2 | 0 | 0 | 3 | 2 | 0 | 11 | 22000
Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 12000
TOTAL | 102 | 62 | 23 | 20 | 22 | 11 | 9 | 249 | 498000
SUCCESS METRICS
Metric | Current | Target | Status | Timeline
Active Tenants | 1 (FMFB) | 5+ | Behind | Week 20+
Revenue Features Live | 1 (Transfers) | 4+ | Behind | Week 27
Frontend Screens | 8 | 27 | Behind | Week 30
API Endpoints | 15 | 35+ | On Track | Week 25
Test Coverage | 297 tests | 500+ tests | On Track | Week 30
Platform Admin Access | No | Yes | Pending | Week 16
Security Compliance | Framework | Production | In Progress | Week 29
Performance (API) | <500ms | <200ms | Pending | Week 30
NEXT 4 WEEKS PRIORITIES
Week | Focus | Key Deliverables | Team | Success Criteria
Week 11 | JWT Enhancement | Enhanced JWT with role claims + subdomain middleware | Backend | JWT tokens include platform_admin flag
Week 12 | Auth Context Update | Frontend AuthContext with role support + database query scoping | Backend + Frontend | Dynamic UI rendering works
Week 13 | Platform Admin UI | Dashboard + Tenant Management screens | Frontend + Security | Platform admin can view all tenants
Week 14 | Platform Features | Onboarding + Analytics + Billing screens | Frontend | Complete platform admin workflow functional