## OrokiiPay_Project_Dashboard
OROKIIPAY MULTI-TENANT BANKING PLATFORM - PROJECT DASHBOARD
PROJECT OVERVIEW
Metric | Value | Target | Status
Total Tasks | 109 | 109 | On Track
Completed Tasks | 14 | 14 | 100%
In Progress Tasks | 0 | 95 | Not Started
Overall Completion | 12.8% | 100% | 58% (with backend weight)
Estimated Completion Week | Week 34 | Week 34 | On Schedule
Current Phase | Phase 1 | Phase 3D | Planning
PHASE COMPLETION STATUS
Phase | Total Tasks | Completed | In Progress | Not Started | % Complete | Timeline
Completed Work | 14 | 14 | 0 | 0 | 100% | Weeks 1-10
Phase 1 - Platform Administration | 15 | 0 | 0 | 15 | 0% | Weeks 11-16
Phase 2A - Transaction Reversals | 8 | 0 | 0 | 8 | 0% | Weeks 17-20
Phase 2B - NIBSS Production | 7 | 0 | 0 | 7 | 0% | Weeks 17-23
Phase 2C - Savings Products | 10 | 0 | 0 | 10 | 0% | Weeks 17-23
Phase 2D - Loan Products | 11 | 0 | 0 | 11 | 0% | Weeks 21-27
Phase 3A - Enhanced Transfers | 6 | 0 | 0 | 6 | 0% | Weeks 23-26
Phase 3B - Account Management | 5 | 0 | 0 | 5 | 0% | Weeks 24-27
Phase 3C - Bill Payments | 5 | 0 | 0 | 5 | 0% | Weeks 27-29
Phase 3D - Advanced Features | 5 | 0 | 0 | 5 | 0% | Weeks 27-31
Security Enhancements | 7 | 0 | 0 | 7 | 0% | Weeks 20-29
Third-Party Integrations | 3 | 0 | 0 | 3 | 0% | Weeks 29-34
Optimization | 5 | 0 | 0 | 5 | 0% | Weeks 26-30
Documentation | 4 | 0 | 0 | 4 | 0% | Weeks 28-32
PRIORITY BREAKDOWN
Priority Level | Task Count | Completed | Outstanding | % of Total
Critical | 43 | 8 | 35 | 39.4%
High | 39 | 5 | 34 | 35.8%
Medium | 23 | 1 | 22 | 21.1%
Low | 4 | 0 | 4 | 3.7%
COMPONENT COMPLETION STATUS
Component | % Complete | Status | Notes
Backend Infrastructure | 87% | Mostly Complete | Core APIs functional
Frontend Screens | 35% | In Progress | 8 of 27 screens done
Design System | 100% | Complete | Production ready
Testing Framework | 100% | Complete | Production ready
AI System | 100% | Complete | Production ready
Cloud Deployment | 100% | Complete | Production ready
Platform Admin | 0% | Not Started | Highest priority
Revenue Features (Savings/Loans) | 10% | Not Started | High business value
Security (Production) | 40% | Partial | Needs enhancement
Multi-Language | 100% | Complete | 4 languages supported
Multi-Currency | 100% | Complete | 6 currencies supported
TEAM WORKLOAD ALLOCATION
Team | Assigned Tasks | % of Total Work | Critical Path | Notes
Backend Team | 45 | 41.3% | Yes | Platform admin APIs + NIBSS + Savings/Loans
Frontend Team | 35 | 32.1% | Yes | 19 screens outstanding
Security Team | 7 | 6.4% | Yes | Production security critical
AI Team | 3 | 2.8% | No | Fraud detection + credit scoring
DevOps Team | 3 | 2.8% | No | Infrastructure optimization
QA Team | 8 | 7.3% | Yes | Testing for all new features
Compliance Team | 1 | 0.9% | Yes | CBN compliance
Business Team | 1 | 0.9% | No | NIBSS credentials
Product Team | 3 | 2.8% | No | Documentation
Design Team | 0 | 0% | No | Design system complete
RISK ASSESSMENT
Risk Category | Risk Level | Mitigation Status | Impact
NIBSS Production Credentials | High | Pending | Delays Phase 2B
Credit Bureau Integration | Medium | Pending | Delays Phase 2D
Platform Admin Complexity | High | Planning Complete | Schedule risk
Frontend Screen Conversion | Medium | Well Defined | Resource risk
Security Compliance | High | Framework Ready | Regulatory risk
Team Capacity | Medium | Manageable | Schedule risk
Third-Party Dependencies | Medium | Identified | Feature risk
MILESTONE TIMELINE
Milestone | Target Week | Status | Dependencies
Platform Admin Complete | Week 16 | Not Started | Phase 1 tasks
Transaction Reversals Live | Week 20 | Not Started | Phase 2A tasks
NIBSS Production Integration | Week 23 | Not Started | NIBSS credentials
Savings Products Live | Week 23 | Not Started | Phase 2C tasks
Loan Products Live | Week 27 | Not Started | Credit bureau + Phase 2D
Enhanced Transfers Complete | Week 26 | Not Started | Phase 3A tasks
Bill Payments Live | Week 29 | Not Started | Biller integrations
Security Hardening Complete | Week 29 | Not Started | Security tasks
Performance Optimization | Week 30 | Not Started | Optimization tasks
Full Platform Launch | Week 34 | Not Started | All phases complete
REVENUE IMPACT FEATURES
Feature | Priority | Business Value | Completion % | Target Week | Revenue Impact
Savings Products | Critical | Very High | 0% | Week 23 | High - Interest margin
Loan Products | Critical | Highest | 0% | Week 27 | Highest - Loan interest
Transaction Reversals | Critical | High | 0% | Week 20 | Medium - Compliance + service
NIBSS Integration | Critical | High | 10% | Week 23 | High - Interbank fees
Bill Payments | High | Medium | 0% | Week 29 | Medium - Transaction fees
Platform Admin | Critical | Very High | 0% | Week 16 | Critical - Multi-tenant revenue
Enhanced Transfers | High | Medium | 0% | Week 26 | Low - Improved UX
OUTSTANDING WORK BY CATEGORY
Category | Tasks | Weeks Required | Priority Level | Team Dependencies
Platform Administration | 15 | 6 weeks | Critical | Backend + Frontend + Security
Revenue Features | 29 | 11 weeks | Critical | Backend + Frontend + AI
Core Banking Features | 16 | 7 weeks | High | Backend + Frontend
Security Hardening | 7 | 9 weeks | Critical | Security + DevOps
Third-Party Integrations | 3 | 6 weeks | Medium | Backend
Optimization | 5 | 5 weeks | High | Backend + DevOps + QA
Documentation | 4 | 5 weeks | Low | Product
WEEKLY RESOURCE REQUIREMENTS
Week Range | Backend FTE | Frontend FTE | Security FTE | QA FTE | Total FTE | Focus Area
Weeks 11-16 | 2 | 2 | 1 | 0.5 | 5.5 | Platform Administration
Weeks 17-20 | 3 | 2 | 0.5 | 1 | 6.5 | Reversals + NIBSS + Savings
Weeks 21-27 | 3 | 3 | 1 | 1 | 8 | Loans + Savings + Transfers
Weeks 28-31 | 2 | 2 | 1 | 1 | 6 | Bill Payments + Advanced Features
Weeks 32-34 | 1 | 1 | 0.5 | 1 | 3.5 | Optimization + Documentation
KEY DEPENDENCIES
Dependency Type | Dependent Tasks | Blocking Item | Risk Level | Mitigation
External - NIBSS | 7 tasks | NIBSS credentials | High | Engage business team now
External - Credit Bureau | 4 tasks | CRC integration | Medium | Start negotiations early
Internal - Platform Admin | All Phase 2-3 tasks | JWT + subdomain routing | Critical | Complete Phase 1 first
Internal - Database Schema | All feature tasks | Migration testing | Medium | Rigorous testing
Internal - Team Capacity | All tasks | Resource availability | Medium | Prioritize critical path
ESTIMATED PROJECT COSTS (Person-Weeks)
Phase | Backend | Frontend | Security | AI | QA | DevOps | Product | Total PW | Cost Estimate
Completed | 48 | 24 | 8 | 12 | 9 | 6 | 3 | 110 | 220000
Phase 1 | 8 | 8 | 2 | 0 | 1 | 0 | 0 | 19 | 38000
Phase 2 (All) | 24 | 16 | 1 | 6 | 4 | 0 | 0 | 51 | 102000
Phase 3 (All) | 12 | 12 | 0 | 0 | 3 | 0 | 0 | 27 | 54000
Security | 0 | 0 | 12 | 2 | 2 | 3 | 0 | 19 | 38000
Integration | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 12000
Optimization | 4 | 2 | 0 | 0 | 3 | 2 | 0 | 11 | 22000
Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 12000
TOTAL | 102 | 62 | 23 | 20 | 22 | 11 | 9 | 249 | 498000
SUCCESS METRICS
Metric | Current | Target | Status | Timeline
Active Tenants | 1 (FMFB) | 5+ | Behind | Week 20+
Revenue Features Live | 1 (Transfers) | 4+ | Behind | Week 27
Frontend Screens | 8 | 27 | Behind | Week 30
API Endpoints | 15 | 35+ | On Track | Week 25
Test Coverage | 297 tests | 500+ tests | On Track | Week 30
Platform Admin Access | No | Yes | Pending | Week 16
Security Compliance | Framework | Production | In Progress | Week 29
Performance (API) | <500ms | <200ms | Pending | Week 30
NEXT 4 WEEKS PRIORITIES
Week | Focus | Key Deliverables | Team | Success Criteria
Week 11 | JWT Enhancement | Enhanced JWT with role claims + subdomain middleware | Backend | JWT tokens include platform_admin flag
Week 12 | Auth Context Update | Frontend AuthContext with role support + database query scoping | Backend + Frontend | Dynamic UI rendering works
Week 13 | Platform Admin UI | Dashboard + Tenant Management screens | Frontend + Security | Platform admin can view all tenants
Week 14 | Platform Features | Onboarding + Analytics + Billing screens | Frontend | Complete platform admin workflow functional

## OrokiiPay_Project_Plan
Phase | Task ID | Task Name | Description | Priority | Status | Start Week | Duration (Weeks) | End Week | % Complete | Owner | Dependencies | Deliverables | Notes
COMPLETED | COMP-001 | Multi-Tenant Database Architecture | Database-per-tenant isolation with platform and tenant databases | Critical | Complete | 1 | 8 | 8 | 100% | Backend Team |  | PostgreSQL setup with multi-tenant schemas | Production ready
COMPLETED | COMP-002 | JWT Authentication System | JWT auth with refresh tokens and multi-tenant context | Critical | Complete | 2 | 4 | 5 | 100% | Backend Team | COMP-001 | Auth endpoints and middleware | Production ready
COMPLETED | COMP-003 | Core API Endpoints | Auth/users/wallets/transfers/transactions APIs | Critical | Complete | 3 | 6 | 8 | 100% | Backend Team | COMP-002 | RESTful API endpoints | Production ready
COMPLETED | COMP-004 | Modern Dashboard UI | AI-integrated dashboard with glassmorphic design | High | Complete | 5 | 3 | 7 | 100% | Frontend Team | COMP-002 | Dashboard screen component | Production ready
COMPLETED | COMP-005 | Transfer System UI | Money transfer flow (internal/external/bill payment) | High | Complete | 6 | 4 | 9 | 100% | Frontend Team | COMP-003 | Transfer screens and flows | Production ready
COMPLETED | COMP-006 | AI Chat Interface | Conversational AI with voice support and smart suggestions | High | Complete | 7 | 4 | 10 | 100% | AI Team | COMP-002 | AI assistant integration | Production ready
COMPLETED | COMP-007 | Design System | Comprehensive UI design system (1700+ CSS classes) | Critical | Complete | 4 | 6 | 9 | 100% | Design Team |  | Design system documentation and components | Production ready
COMPLETED | COMP-008 | Testing Framework | 4-layer testing architecture (Unit/Integration/UX/E2E) | Critical | Complete | 8 | 3 | 10 | 100% | QA Team |  | Testing infrastructure and 297 tests | Production ready
COMPLETED | COMP-009 | Cloud Deployment | GCP deployment with SSL and fast deployment system | Critical | Complete | 9 | 2 | 10 | 100% | DevOps Team | COMP-001 | Production environment on 34.59.143.25 | Production ready
COMPLETED | COMP-010 | Multi-Language Support | 4 languages (en/fr/de/es) with i18n | Medium | Complete | 9 | 2 | 10 | 100% | Frontend Team |  | Translation files and i18n config | Production ready
COMPLETED | COMP-011 | Multi-Currency Support | 6 currencies with locale-specific formatting | Medium | Complete | 9 | 2 | 10 | 100% | Backend Team |  | Currency formatting utilities | Production ready
COMPLETED | COMP-012 | Transaction History UI | Transaction list and detail screens | High | Complete | 6 | 2 | 7 | 100% | Frontend Team | COMP-003 | Transaction history screens | Production ready
COMPLETED | COMP-013 | Authentication UI | Login and registration screens | Critical | Complete | 5 | 2 | 6 | 100% | Frontend Team | COMP-002 | Auth screens | Production ready
COMPLETED | COMP-014 | Security Screens | Biometric and PIN security screens | Medium | Complete | 7 | 2 | 8 | 100% | Frontend Team | COMP-002 | Security setup screens | Production ready
PHASE 1 | P1-001 | JWT Role Claims Enhancement | Add platform_admin and permission claims to JWT | Critical | Not Started | 11 | 1 | 11 | 0% | Backend Team | COMP-002 | Enhanced JWT structure | Required for platform admin access
PHASE 1 | P1-002 | Subdomain Detection Middleware | Implement subdomain routing (admin vs tenant) | Critical | Not Started | 11 | 1 | 11 | 0% | Backend Team | P1-001 | Subdomain middleware | Core platform admin feature
PHASE 1 | P1-003 | Role-Based Authorization Middleware | Create middleware for role and permission checks | Critical | Not Started | 11 | 1 | 11 | 0% | Backend Team | P1-001 | Auth middleware enhancements | Security critical
PHASE 1 | P1-004 | Database Query Context Injection | Automatic tenant scoping in database queries | Critical | Not Started | 11 | 2 | 12 | 0% | Backend Team | P1-002 | Database service layer | Prevents cross-tenant data leaks
PHASE 1 | P1-005 | Enhanced Auth Context (Frontend) | Update AuthContext with role-based state | Critical | Not Started | 12 | 1 | 12 | 0% | Frontend Team | P1-001 | Enhanced AuthContext component | Frontend foundation
PHASE 1 | P1-006 | Dynamic UI Rendering System | Component system that adapts to user role | Critical | Not Started | 12 | 2 | 13 | 0% | Frontend Team | P1-005 | HOC and utility components | Core UI architecture
PHASE 1 | P1-007 | Platform Admin Dashboard Screen | Cross-tenant metrics and overview dashboard | Critical | Not Started | 13 | 2 | 14 | 0% | Frontend Team | P1-006 | Platform dashboard component | First admin screen
PHASE 1 | P1-008 | Tenant Management Screen | List/view/edit all tenants interface | Critical | Not Started | 13 | 2 | 14 | 0% | Frontend Team | P1-006 | Tenant management UI | Core admin functionality
PHASE 1 | P1-009 | Tenant Onboarding Workflow Screen | New bank approval and provisioning workflow | High | Not Started | 14 | 2 | 15 | 0% | Frontend Team | P1-008 | Onboarding workflow screens | Business critical
PHASE 1 | P1-010 | Platform Analytics Screen | Revenue tracking and business intelligence | High | Not Started | 14 | 2 | 15 | 0% | Frontend Team | P1-007 | Analytics dashboard | Revenue visibility
PHASE 1 | P1-011 | System Health Monitoring Screen | Platform monitoring and maintenance interface | High | Not Started | 15 | 1 | 15 | 0% | Frontend Team | P1-007 | System health dashboard | Operations critical
PHASE 1 | P1-012 | Billing Management Screen | Subscription and usage-based billing | High | Not Started | 15 | 2 | 16 | 0% | Frontend Team | P1-010 | Billing management UI | Revenue management
PHASE 1 | P1-013 | Enhanced Security for Platform Admin | MFA and IP restriction for admin access | Critical | Not Started | 13 | 2 | 14 | 0% | Security Team | P1-003 | MFA implementation | Security requirement
PHASE 1 | P1-014 | Platform Admin API Endpoints | Backend APIs for platform admin features | Critical | Not Started | 12 | 3 | 14 | 0% | Backend Team | P1-004 | Platform admin APIs | Required for admin UI
PHASE 1 | P1-015 | Integration Testing - Platform Admin | Test platform admin features across all layers | Critical | Not Started | 16 | 1 | 16 | 0% | QA Team | P1-012 | Test suite for platform admin | Quality gate
PHASE 2A | P2A-001 | Transaction Reversal Data Model | Database schema for reversal tracking | Critical | Not Started | 17 | 1 | 17 | 0% | Backend Team | COMP-001 | Reversal tables and migrations | CBN compliance requirement
PHASE 2A | P2A-002 | Reversal Workflow Engine | State machine for reversal lifecycle | Critical | Not Started | 17 | 2 | 18 | 0% | Backend Team | P2A-001 | Reversal processing engine | Core reversal logic
PHASE 2A | P2A-003 | CBN Reversal Compliance Module | Ensure CBN regulatory compliance | Critical | Not Started | 18 | 2 | 19 | 0% | Compliance Team | P2A-002 | Compliance validation module | Regulatory requirement
PHASE 2A | P2A-004 | AI Reversal Pattern Analysis | ML-based fraud detection for reversals | High | Not Started | 18 | 2 | 19 | 0% | AI Team | P2A-002 | AI pattern detection | Fraud prevention
PHASE 2A | P2A-005 | Reversal Management Screen (Admin) | Platform admin reversal oversight interface | High | Not Started | 19 | 2 | 20 | 0% | Frontend Team | P2A-002 | Admin reversal dashboard | Operations tool
PHASE 2A | P2A-006 | Reversal Management Screen (Tenant) | Bank-specific reversal management | High | Not Started | 19 | 2 | 20 | 0% | Frontend Team | P2A-002 | Tenant reversal screens | Customer service tool
PHASE 2A | P2A-007 | Reversal API Endpoints | REST APIs for reversal operations | Critical | Not Started | 17 | 2 | 18 | 0% | Backend Team | P2A-001 | Reversal APIs | Required for UI
PHASE 2A | P2A-008 | Reversal Testing Suite | Comprehensive tests for reversal system | Critical | Not Started | 20 | 1 | 20 | 0% | QA Team | P2A-006 | Reversal test suite | Quality assurance
PHASE 2B | P2B-001 | NIBSS Production Credentials | Obtain live NIBSS API credentials | Critical | Not Started | 17 | 2 | 18 | 0% | Business Team |  | NIBSS production access | External dependency
PHASE 2B | P2B-002 | NIBSS Name Enquiry (Production) | Implement live name enquiry integration | Critical | Not Started | 19 | 2 | 20 | 0% | Backend Team | P2B-001 | Name enquiry service | Core banking feature
PHASE 2B | P2B-003 | NIBSS Fund Transfer (Production) | Implement live fund transfer integration | Critical | Not Started | 19 | 3 | 21 | 0% | Backend Team | P2B-002 | Fund transfer service | Revenue critical
PHASE 2B | P2B-004 | NIBSS Transaction Status Query | Implement transaction status checking | High | Not Started | 20 | 2 | 21 | 0% | Backend Team | P2B-002 | Status query service | Operations requirement
PHASE 2B | P2B-005 | NIBSS Error Handling & Retry | Robust error handling and retry logic | Critical | Not Started | 21 | 2 | 22 | 0% | Backend Team | P2B-003 | Error handling framework | Production stability
PHASE 2B | P2B-006 | NIBSS Integration Testing | End-to-end testing with NIBSS sandbox | Critical | Not Started | 21 | 1 | 21 | 0% | QA Team | P2B-003 | NIBSS test suite | Quality gate
PHASE 2B | P2B-007 | External Transfer Screen Enhancement | UI for NIBSS interbank transfers | High | Not Started | 22 | 2 | 23 | 0% | Frontend Team | P2B-003 | Enhanced transfer screens | User experience
PHASE 2C | P2C-001 | Savings Account Data Model | Database schema for savings products | Critical | Not Started | 17 | 1 | 17 | 0% | Backend Team | COMP-001 | Savings tables and migrations | Foundation for savings
PHASE 2C | P2C-002 | Interest Calculation Engine | Automated interest calculation and posting | Critical | Not Started | 18 | 2 | 19 | 0% | Backend Team | P2C-001 | Interest engine | Revenue generation
PHASE 2C | P2C-003 | Savings Product Configuration | Tenant-specific savings product setup | High | Not Started | 18 | 2 | 19 | 0% | Backend Team | P2C-001 | Product config system | Multi-tenant flexibility
PHASE 2C | P2C-004 | Regular Savings Screen | Basic savings account interface | High | Not Started | 19 | 2 | 20 | 0% | Frontend Team | P2C-002 | Regular savings UI | Entry-level product
PHASE 2C | P2C-005 | High-Yield Savings Screen | Premium savings with tier rates | High | Not Started | 20 | 2 | 21 | 0% | Frontend Team | P2C-002 | High-yield savings UI | Premium product
PHASE 2C | P2C-006 | Goal-Based Savings Screen | Target savings with progress tracking | High | Not Started | 20 | 2 | 21 | 0% | Frontend Team | P2C-002 | Goal savings UI | Customer engagement
PHASE 2C | P2C-007 | Locked Savings Screen | Time-locked savings with penalties | High | Not Started | 21 | 2 | 22 | 0% | Frontend Team | P2C-002 | Locked savings UI | High-yield product
PHASE 2C | P2C-008 | Savings API Endpoints | REST APIs for savings operations | Critical | Not Started | 18 | 2 | 19 | 0% | Backend Team | P2C-001 | Savings APIs | Required for UI
PHASE 2C | P2C-009 | Savings Testing Suite | Comprehensive savings product tests | Critical | Not Started | 22 | 1 | 22 | 0% | QA Team | P2C-007 | Savings test suite | Quality assurance
PHASE 2C | P2C-010 | Savings Analytics Dashboard | Platform and tenant savings analytics | Medium | Not Started | 22 | 2 | 23 | 0% | Frontend Team | P2C-002 | Analytics screens | Business intelligence
PHASE 2D | P2D-001 | Loan Account Data Model | Database schema for loan products | Critical | Not Started | 21 | 1 | 21 | 0% | Backend Team | COMP-001 | Loan tables and migrations | Foundation for loans
PHASE 2D | P2D-002 | Credit Bureau Integration | CRC Credit Bureau API integration | Critical | Not Started | 22 | 3 | 24 | 0% | Backend Team | P2D-001 | Credit bureau service | Risk management
PHASE 2D | P2D-003 | AI Credit Scoring Engine | ML-based credit scoring system | High | Not Started | 22 | 3 | 24 | 0% | AI Team | P2D-002 | AI scoring model | Competitive advantage
PHASE 2D | P2D-004 | Loan Approval Workflow | Automated loan approval state machine | Critical | Not Started | 23 | 2 | 24 | 0% | Backend Team | P2D-003 | Approval workflow engine | Core loan logic
PHASE 2D | P2D-005 | Loan Repayment Engine | Automated repayment processing | Critical | Not Started | 24 | 2 | 25 | 0% | Backend Team | P2D-001 | Repayment processing | Revenue collection
PHASE 2D | P2D-006 | Personal Loan Screen | Individual loan application interface | High | Not Started | 24 | 2 | 25 | 0% | Frontend Team | P2D-004 | Personal loan UI | Mass market product
PHASE 2D | P2D-007 | Business Loan Screen | SME loan with enhanced KYC | High | Not Started | 25 | 2 | 26 | 0% | Frontend Team | P2D-004 | Business loan UI | High-value product
PHASE 2D | P2D-008 | Quick Loan Screen | Instant micro-loan interface | High | Not Started | 25 | 2 | 26 | 0% | Frontend Team | P2D-003 | Quick loan UI | Customer convenience
PHASE 2D | P2D-009 | Loan API Endpoints | REST APIs for loan operations | Critical | Not Started | 22 | 2 | 23 | 0% | Backend Team | P2D-001 | Loan APIs | Required for UI
PHASE 2D | P2D-010 | Loan Testing Suite | Comprehensive loan product tests | Critical | Not Started | 26 | 1 | 26 | 0% | QA Team | P2D-008 | Loan test suite | Quality assurance
PHASE 2D | P2D-011 | Loan Analytics Dashboard | Platform and tenant loan analytics | Medium | Not Started | 26 | 2 | 27 | 0% | Frontend Team | P2D-004 | Loan analytics UI | Risk monitoring
PHASE 3A | P3A-001 | Bulk Transfer Data Model | Schema for batch transfer processing | High | Not Started | 23 | 1 | 23 | 0% | Backend Team | COMP-003 | Bulk transfer tables | Efficiency feature
PHASE 3A | P3A-002 | Transfer Templates System | Save and reuse recipient details | High | Not Started | 23 | 2 | 24 | 0% | Backend Team | COMP-003 | Template management | User convenience
PHASE 3A | P3A-003 | Scheduled Transfer Engine | Recurring and future-dated transfers | High | Not Started | 24 | 2 | 25 | 0% | Backend Team | COMP-003 | Scheduling engine | Advanced feature
PHASE 3A | P3A-004 | Bulk Transfer Screen | Multiple transfer processing UI | High | Not Started | 25 | 2 | 26 | 0% | Frontend Team | P3A-001 | Bulk transfer interface | Business feature
PHASE 3A | P3A-005 | Transfer Templates Screen | Beneficiary management interface | High | Not Started | 25 | 2 | 26 | 0% | Frontend Team | P3A-002 | Template management UI | User experience
PHASE 3A | P3A-006 | Enhanced Transfer Testing | Tests for advanced transfer features | High | Not Started | 26 | 1 | 26 | 0% | QA Team | P3A-005 | Transfer test suite | Quality assurance
PHASE 3B | P3B-001 | Multi-Account Data Model | Support multiple accounts per user | Medium | Not Started | 24 | 1 | 24 | 0% | Backend Team | COMP-001 | Account relationship tables | Advanced banking
PHASE 3B | P3B-002 | Joint Account Management | Shared account functionality | Medium | Not Started | 25 | 2 | 26 | 0% | Backend Team | P3B-001 | Joint account logic | Family banking
PHASE 3B | P3B-003 | Account Switching UI | Interface to switch between accounts | Medium | Not Started | 26 | 2 | 27 | 0% | Frontend Team | P3B-001 | Account switcher component | User experience
PHASE 3B | P3B-004 | Multi-Account Management Screen | Overview of all user accounts | Medium | Not Started | 26 | 2 | 27 | 0% | Frontend Team | P3B-001 | Account overview UI | Convenience feature
PHASE 3B | P3B-005 | KYC Enhancement | Enhanced KYC workflow for compliance | High | Not Started | 24 | 3 | 26 | 0% | Backend Team | COMP-002 | Enhanced KYC system | Regulatory requirement
PHASE 3C | P3C-001 | Biller Integration | Nigerian biller network integration | High | Not Started | 27 | 3 | 29 | 0% | Backend Team | COMP-003 | Biller API integrations | Revenue opportunity
PHASE 3C | P3C-002 | Bill Payment Categories | Organize billers by category | Medium | Not Started | 27 | 1 | 27 | 0% | Backend Team | P3C-001 | Category management | User experience
PHASE 3C | P3C-003 | Recurring Bill Payments | Automated recurring payments | High | Not Started | 28 | 2 | 29 | 0% | Backend Team | P3C-001 | Recurring payment engine | Customer retention
PHASE 3C | P3C-004 | Bill Payments Screen | Comprehensive biller interface | High | Not Started | 28 | 2 | 29 | 0% | Frontend Team | P3C-001 | Bill payment UI | Customer convenience
PHASE 3C | P3C-005 | Bill Payment History | Transaction history for bill payments | Medium | Not Started | 29 | 1 | 29 | 0% | Frontend Team | P3C-004 | History screen | User tracking
PHASE 3D | P3D-001 | Save-as-You-Transact Engine | Automated savings on transactions | Medium | Not Started | 27 | 2 | 28 | 0% | Backend Team | P2C-001 | Auto-save logic | Innovation feature
PHASE 3D | P3D-002 | Save-as-You-Transact Screen | Configuration and tracking UI | Medium | Not Started | 28 | 2 | 29 | 0% | Frontend Team | P3D-001 | Auto-save UI | Customer engagement
PHASE 3D | P3D-003 | Advanced Reporting Engine | Customizable reports for tenants | Medium | Not Started | 28 | 3 | 30 | 0% | Backend Team | COMP-003 | Reporting engine | Business intelligence
PHASE 3D | P3D-004 | Report Builder Screen | Custom report generation UI | Medium | Not Started | 29 | 2 | 30 | 0% | Frontend Team | P3D-003 | Report builder interface | Admin tool
PHASE 3D | P3D-005 | Customer Support Integration | Ticketing and support system | Low | Not Started | 30 | 2 | 31 | 0% | Backend Team | COMP-002 | Support system | Customer service
SECURITY | SEC-001 | Production 2FA/MFA | Two-factor authentication for all users | Critical | Not Started | 20 | 3 | 22 | 0% | Security Team | COMP-002 | MFA system | Security requirement
SECURITY | SEC-002 | Enhanced Biometric Auth | Improved biometric authentication | High | Not Started | 22 | 2 | 23 | 0% | Security Team | COMP-014 | Biometric enhancements | User convenience
SECURITY | SEC-003 | HSM Key Management | Hardware security module integration | Critical | Not Started | 23 | 4 | 26 | 0% | Security Team | COMP-001 | HSM integration | Production security
SECURITY | SEC-004 | WAF Protection | Web Application Firewall deployment | Critical | Not Started | 24 | 3 | 26 | 0% | DevOps Team | COMP-009 | WAF configuration | Attack prevention
SECURITY | SEC-005 | Enhanced Fraud Detection | Production AI fraud detection | High | Not Started | 25 | 4 | 28 | 0% | AI Team | COMP-006 | Fraud detection system | Risk management
SECURITY | SEC-006 | Penetration Testing | Security audit and pen testing | Critical | Not Started | 28 | 2 | 29 | 0% | Security Team | SEC-004 | Security audit report | Compliance requirement
SECURITY | SEC-007 | Security Monitoring Dashboard | Real-time security monitoring | High | Not Started | 26 | 2 | 27 | 0% | Security Team | SEC-003 | Monitoring dashboard | Operations tool
INTEGRATION | INT-001 | Paystack Integration | Payment gateway integration | Medium | Not Started | 29 | 3 | 31 | 0% | Backend Team | COMP-003 | Paystack service | Payment option
INTEGRATION | INT-002 | Investment Platform APIs | Third-party investment integrations | Low | Not Started | 30 | 4 | 33 | 0% | Backend Team | COMP-003 | Investment APIs | Product diversification
INTEGRATION | INT-003 | Insurance Product APIs | Insurance product integrations | Low | Not Started | 31 | 4 | 34 | 0% | Backend Team | COMP-003 | Insurance APIs | Product diversification
OPTIMIZATION | OPT-001 | Performance Optimization | Database and API performance tuning | High | Not Started | 26 | 3 | 28 | 0% | Backend Team | P2D-005 | Performance improvements | User experience
OPTIMIZATION | OPT-002 | Mobile Optimization | Native mobile app enhancements | Medium | Not Started | 28 | 2 | 29 | 0% | Frontend Team | COMP-005 | Mobile optimizations | User experience
OPTIMIZATION | OPT-003 | Caching Strategy | Redis caching implementation | High | Not Started | 27 | 2 | 28 | 0% | Backend Team | OPT-001 | Caching layer | Performance boost
OPTIMIZATION | OPT-004 | Load Testing | Performance testing at scale | High | Not Started | 29 | 2 | 30 | 0% | QA Team | OPT-001 | Load test results | Production readiness
OPTIMIZATION | OPT-005 | CDN Implementation | Content delivery network setup | Medium | Not Started | 30 | 1 | 30 | 0% | DevOps Team | COMP-009 | CDN configuration | Global performance
DOCUMENTATION | DOC-001 | API Documentation | Comprehensive API documentation | Medium | Not Started | 28 | 2 | 29 | 0% | Backend Team | P2D-009 | API docs | Developer experience
DOCUMENTATION | DOC-002 | User Guides | End-user documentation | Low | Not Started | 30 | 3 | 32 | 0% | Product Team | P2D-008 | User guides | Customer support
DOCUMENTATION | DOC-003 | Admin Guides | Platform admin documentation | Medium | Not Started | 29 | 2 | 30 | 0% | Product Team | P1-012 | Admin guides | Operations support
DOCUMENTATION | DOC-004 | Tenant Onboarding Docs | New tenant setup documentation | Medium | Not Started | 30 | 2 | 31 | 0% | Product Team | P1-009 | Onboarding docs | Business enablement

## OrokiiPay_Timeline_Gantt
OROKIIPAY PROJECT TIMELINE - GANTT CHART VIEW
Task/Phase | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34
COMPLETED: Multi-Tenant Database | Week 1: ‚ñ†; Week 2: ‚ñ†; Week 3: ‚ñ†; Week 4: ‚ñ†; Week 5: ‚ñ†; Week 6: ‚ñ†; Week 7: ‚ñ†; Week 8: ‚ñ†
COMPLETED: JWT Authentication | Week 2: ‚ñ†; Week 3: ‚ñ†; Week 4: ‚ñ†; Week 5: ‚ñ†
COMPLETED: Core APIs | Week 3: ‚ñ†; Week 4: ‚ñ†; Week 5: ‚ñ†; Week 6: ‚ñ†; Week 7: ‚ñ†; Week 8: ‚ñ†
COMPLETED: Dashboard UI | Week 5: ‚ñ†; Week 6: ‚ñ†; Week 7: ‚ñ†
COMPLETED: Transfer UI | Week 6: ‚ñ†; Week 7: ‚ñ†; Week 8: ‚ñ†; Week 9: ‚ñ†
COMPLETED: AI Chat | Week 7: ‚ñ†; Week 8: ‚ñ†; Week 9: ‚ñ†; Week 10: ‚ñ†
COMPLETED: Design System | Week 4: ‚ñ†; Week 5: ‚ñ†; Week 6: ‚ñ†; Week 7: ‚ñ†; Week 8: ‚ñ†; Week 9: ‚ñ†
COMPLETED: Testing Framework | Week 8: ‚ñ†; Week 9: ‚ñ†; Week 10: ‚ñ†
COMPLETED: Cloud Deployment | Week 9: ‚ñ†; Week 10: ‚ñ†
COMPLETED: Multi-Language | Week 9: ‚ñ†; Week 10: ‚ñ†
COMPLETED: Multi-Currency | Week 9: ‚ñ†; Week 10: ‚ñ†
Phase 1: JWT Role Enhancement | Week 11: ‚ñ†
Phase 1: Subdomain Middleware | Week 11: ‚ñ†
Phase 1: Auth Middleware | Week 11: ‚ñ†
Phase 1: DB Query Context | Week 11: ‚ñ†; Week 12: ‚ñ†
Phase 1: Enhanced Auth Context | Week 12: ‚ñ†
Phase 1: Dynamic UI Rendering | Week 13: ‚ñ†; Week 14: ‚ñ†
Phase 1: Platform Dashboard | Week 14: ‚ñ†; Week 15: ‚ñ†
Phase 1: Tenant Management | Week 13: ‚ñ†; Week 14: ‚ñ†
Phase 1: Onboarding Workflow | Week 16: ‚ñ†; Week 17: ‚ñ†
Phase 1: Platform Analytics | Week 15: ‚ñ†; Week 16: ‚ñ†
Phase 1: System Health | Week 16: ‚ñ†
Phase 1: Billing Management | Week 15: ‚ñ†; Week 16: ‚ñ†
Phase 1: Enhanced Security | Week 14: ‚ñ†; Week 15: ‚ñ†
Phase 1: Platform APIs | Week 13: ‚ñ†; Week 14: ‚ñ†; Week 15: ‚ñ†
Phase 1: Integration Testing | Week 18: ‚ñ†
Phase 2A: Reversal Data Model | Week 17: ‚ñ†
Phase 2A: Reversal Workflow | Week 17: ‚ñ†; Week 18: ‚ñ†
Phase 2A: CBN Compliance | Week 18: ‚ñ†; Week 19: ‚ñ†
Phase 2A: AI Pattern Analysis | Week 18: ‚ñ†; Week 19: ‚ñ†
Phase 2A: Admin Reversal Screen | Week 19: ‚ñ†; Week 20: ‚ñ†
Phase 2A: Tenant Reversal Screen | Week 19: ‚ñ†; Week 20: ‚ñ†
Phase 2A: Reversal APIs | Week 17: ‚ñ†; Week 18: ‚ñ†
Phase 2A: Reversal Testing | Week 20: ‚ñ†
Phase 2B: NIBSS Credentials | Week 17: ‚ñ†; Week 18: ‚ñ†
Phase 2B: Name Enquiry | Week 19: ‚ñ†; Week 20: ‚ñ†
Phase 2B: Fund Transfer | Week 19: ‚ñ†; Week 20: ‚ñ†; Week 21: ‚ñ†
Phase 2B: Status Query | Week 20: ‚ñ†; Week 21: ‚ñ†
Phase 2B: Error Handling | Week 21: ‚ñ†; Week 22: ‚ñ†
Phase 2B: NIBSS Testing | Week 21: ‚ñ†
Phase 2B: Transfer Screen Enhancement | Week 22: ‚ñ†; Week 23: ‚ñ†
Phase 2C: Savings Data Model | Week 17: ‚ñ†
Phase 2C: Interest Engine | Week 18: ‚ñ†; Week 19: ‚ñ†
Phase 2C: Product Configuration | Week 18: ‚ñ†; Week 19: ‚ñ†
Phase 2C: Regular Savings | Week 19: ‚ñ†; Week 20: ‚ñ†
Phase 2C: High-Yield Savings | Week 20: ‚ñ†; Week 21: ‚ñ†
Phase 2C: Goal Savings | Week 20: ‚ñ†; Week 21: ‚ñ†
Phase 2C: Locked Savings | Week 21: ‚ñ†; Week 22: ‚ñ†
Phase 2C: Savings APIs | Week 18: ‚ñ†; Week 19: ‚ñ†
Phase 2C: Savings Testing | Week 22: ‚ñ†
Phase 2C: Savings Analytics | Week 22: ‚ñ†; Week 23: ‚ñ†
Phase 2D: Loan Data Model | Week 21: ‚ñ†
Phase 2D: Credit Bureau | Week 23: ‚ñ†; Week 24: ‚ñ†; Week 25: ‚ñ†
Phase 2D: AI Credit Scoring | Week 23: ‚ñ†; Week 24: ‚ñ†; Week 25: ‚ñ†
Phase 2D: Approval Workflow | Week 22: ‚ñ†; Week 23: ‚ñ†
Phase 2D: Repayment Engine | Week 24: ‚ñ†; Week 25: ‚ñ†
Phase 2D: Personal Loan Screen | Week 24: ‚ñ†; Week 25: ‚ñ†
Phase 2D: Business Loan Screen | Week 25: ‚ñ†; Week 26: ‚ñ†
Phase 2D: Quick Loan Screen | Week 25: ‚ñ†; Week 26: ‚ñ†
Phase 2D: Loan APIs | Week 23: ‚ñ†; Week 24: ‚ñ†
Phase 2D: Loan Testing | Week 26: ‚ñ†
Phase 2D: Loan Analytics | Week 26: ‚ñ†; Week 27: ‚ñ†
Phase 3A: Bulk Transfer Data | Week 23: ‚ñ†
Phase 3A: Transfer Templates | Week 23: ‚ñ†; Week 24: ‚ñ†
Phase 3A: Scheduled Transfers | Week 24: ‚ñ†; Week 25: ‚ñ†
Phase 3A: Bulk Transfer Screen | Week 25: ‚ñ†; Week 26: ‚ñ†
Phase 3A: Templates Screen | Week 25: ‚ñ†; Week 26: ‚ñ†
Phase 3A: Transfer Testing | Week 26: ‚ñ†
Phase 3B: Multi-Account Data | Week 24: ‚ñ†
Phase 3B: Joint Account | Week 25: ‚ñ†; Week 26: ‚ñ†
Phase 3B: Account Switching | Week 26: ‚ñ†; Week 27: ‚ñ†
Phase 3B: Multi-Account Screen | Week 26: ‚ñ†; Week 27: ‚ñ†
Phase 3B: KYC Enhancement | Week 24: ‚ñ†; Week 25: ‚ñ†; Week 26: ‚ñ†
Phase 3C: Biller Integration | Week 27: ‚ñ†; Week 28: ‚ñ†; Week 29: ‚ñ†
Phase 3C: Bill Categories | Week 27: ‚ñ†
Phase 3C: Recurring Bills | Week 28: ‚ñ†; Week 29: ‚ñ†
Phase 3C: Bill Payments Screen | Week 28: ‚ñ†; Week 29: ‚ñ†
Phase 3C: Bill History | Week 29: ‚ñ†
Phase 3D: Save-as-You-Transact | Week 27: ‚ñ†; Week 28: ‚ñ†
Phase 3D: Auto-Save Screen | Week 28: ‚ñ†; Week 29: ‚ñ†
Phase 3D: Reporting Engine | Week 28: ‚ñ†; Week 29: ‚ñ†; Week 30: ‚ñ†
Phase 3D: Report Builder | Week 29: ‚ñ†; Week 30: ‚ñ†
Phase 3D: Support Integration | Week 30: ‚ñ†; Week 31: ‚ñ†
Security: 2FA/MFA | Week 20: ‚ñ†; Week 21: ‚ñ†; Week 22: ‚ñ†
Security: Enhanced Biometric | Week 22: ‚ñ†; Week 23: ‚ñ†
Security: HSM Integration | Week 23: ‚ñ†; Week 24: ‚ñ†; Week 25: ‚ñ†; Week 26: ‚ñ†
Security: WAF Protection | Week 24: ‚ñ†; Week 25: ‚ñ†; Week 26: ‚ñ†
Security: Fraud Detection | Week 25: ‚ñ†; Week 26: ‚ñ†; Week 27: ‚ñ†; Week 28: ‚ñ†
Security: Penetration Testing | Week 28: ‚ñ†; Week 29: ‚ñ†
Security: Monitoring Dashboard | Week 26: ‚ñ†; Week 27: ‚ñ†
Integration: Paystack | Week 29: ‚ñ†; Week 30: ‚ñ†; Week 31: ‚ñ†
Integration: Investment Platforms | Week 30: ‚ñ†; Week 31: ‚ñ†; Week 32: ‚ñ†; Week 33: ‚ñ†
Integration: Insurance APIs | Week 31: ‚ñ†; Week 32: ‚ñ†; Week 33: ‚ñ†; Week 34: ‚ñ†
Optimization: Performance | Week 26: ‚ñ†; Week 27: ‚ñ†; Week 28: ‚ñ†
Optimization: Mobile | Week 29: ‚ñ†; Week 30: ‚ñ†
Optimization: Caching | Week 27: ‚ñ†; Week 28: ‚ñ†
Optimization: Load Testing | Week 29: ‚ñ†; Week 30: ‚ñ†
Optimization: CDN | Week 30: ‚ñ†
Documentation: API Docs | Week 28: ‚ñ†; Week 29: ‚ñ†
Documentation: User Guides | Week 30: ‚ñ†; Week 31: ‚ñ†; Week 32: ‚ñ†
Documentation: Admin Guides | Week 29: ‚ñ†; Week 30: ‚ñ†
Documentation: Onboarding Docs | Week 30: ‚ñ†; Week 31: ‚ñ†
MILESTONE MARKERS
Platform Admin Complete | Week 16: ‚ñ†
Transaction Reversals Live | Week 20: ‚ñ†
NIBSS Production Integration | Week 23: ‚ñ†
Savings Products Live | Week 23: ‚ñ†
Loan Products Live | Week 27: ‚ñ†
Enhanced Transfers Complete | Week 26: ‚ñ†
Bill Payments Live | Week 29: ‚ñ†
Security Hardening Complete | Week 29: ‚ñ†
Performance Optimization | Week 30: ‚ñ†
Full Platform Launch | Week 34: ‚ñ†
CRITICAL PATH INDICATOR
Critical Path | [10 empty] | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ†
LEGEND
‚ñ† = Task in progress/planned
Blank = No activity
Critical Path = Backend + Frontend dependent tasks that determine minimum project duration