## OrokiiPay_Timeline_Gantt
OROKIIPAY PROJECT TIMELINE - GANTT CHART VIEW
Task/Phase | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34
COMPLETED: Multi-Tenant Database | Week 1: ‚ñ†; Week 2: ‚ñ†; Week 3: ‚ñ†; Week 4: ‚ñ†; Week 5: ‚ñ†; Week 6: ‚ñ†; Week 7: ‚ñ†; Week 8: ‚ñ†
COMPLETED: JWT Authentication | Week 2: ‚ñ†; Week 3: ‚ñ†; Week 4: ‚ñ†; Week 5: ‚ñ†
COMPLETED: Core APIs | Week 3: ‚ñ†; Week 4: ‚ñ†; Week 5: ‚ñ†; Week 6: ‚ñ†; Week 7: ‚ñ†; Week 8: ‚ñ†
COMPLETED: Dashboard UI | Week 5: ‚ñ†; Week 6: ‚ñ†; Week 7: ‚ñ†
COMPLETED: Transfer UI | Week 6: ‚ñ†; Week 7: ‚ñ†; Week 8: ‚ñ†; Week 9: ‚ñ†
COMPLETED: AI Chat | Week 7: ‚ñ†; Week 8: ‚ñ†; Week 9: ‚ñ†; Week 10: ‚ñ†
COMPLETED: Design System | Week 4: ‚ñ†; Week 5: ‚ñ†; Week 6: ‚ñ†; Week 7: ‚ñ†; Week 8: ‚ñ†; Week 9: ‚ñ†
COMPLETED: Testing Framework | Week 8: ‚ñ†; Week 9: ‚ñ†; Week 10: ‚ñ†
COMPLETED: Cloud Deployment | Week 9: ‚ñ†; Week 10: ‚ñ†
COMPLETED: Multi-Language | Week 9: ‚ñ†; Week 10: ‚ñ†
COMPLETED: Multi-Currency | Week 9: ‚ñ†; Week 10: ‚ñ†
Phase 1: JWT Role Enhancement | Week 11: ‚ñ†
Phase 1: Subdomain Middleware | Week 11: ‚ñ†
Phase 1: Auth Middleware | Week 11: ‚ñ†
Phase 1: DB Query Context | Week 11: ‚ñ†; Week 12: ‚ñ†
Phase 1: Enhanced Auth Context | Week 12: ‚ñ†
Phase 1: Dynamic UI Rendering | Week 13: ‚ñ†; Week 14: ‚ñ†
Phase 1: Platform Dashboard | Week 14: ‚ñ†; Week 15: ‚ñ†
Phase 1: Tenant Management | Week 13: ‚ñ†; Week 14: ‚ñ†
Phase 1: Onboarding Workflow | Week 16: ‚ñ†; Week 17: ‚ñ†
Phase 1: Platform Analytics | Week 15: ‚ñ†; Week 16: ‚ñ†
Phase 1: System Health | Week 16: ‚ñ†
Phase 1: Billing Management | Week 15: ‚ñ†; Week 16: ‚ñ†
Phase 1: Enhanced Security | Week 14: ‚ñ†; Week 15: ‚ñ†
Phase 1: Platform APIs | Week 13: ‚ñ†; Week 14: ‚ñ†; Week 15: ‚ñ†
Phase 1: Integration Testing | Week 18: ‚ñ†
Phase 2A: Reversal Data Model | Week 17: ‚ñ†
Phase 2A: Reversal Workflow | Week 17: ‚ñ†; Week 18: ‚ñ†
Phase 2A: CBN Compliance | Week 18: ‚ñ†; Week 19: ‚ñ†
Phase 2A: AI Pattern Analysis | Week 18: ‚ñ†; Week 19: ‚ñ†
Phase 2A: Admin Reversal Screen | Week 19: ‚ñ†; Week 20: ‚ñ†
Phase 2A: Tenant Reversal Screen | Week 19: ‚ñ†; Week 20: ‚ñ†
Phase 2A: Reversal APIs | Week 17: ‚ñ†; Week 18: ‚ñ†
Phase 2A: Reversal Testing | Week 20: ‚ñ†
Phase 2B: NIBSS Credentials | Week 17: ‚ñ†; Week 18: ‚ñ†
Phase 2B: Name Enquiry | Week 19: ‚ñ†; Week 20: ‚ñ†
Phase 2B: Fund Transfer | Week 19: ‚ñ†; Week 20: ‚ñ†; Week 21: ‚ñ†
Phase 2B: Status Query | Week 20: ‚ñ†; Week 21: ‚ñ†
Phase 2B: Error Handling | Week 21: ‚ñ†; Week 22: ‚ñ†
Phase 2B: NIBSS Testing | Week 21: ‚ñ†
Phase 2B: Transfer Screen Enhancement | Week 22: ‚ñ†; Week 23: ‚ñ†
Phase 2C: Savings Data Model | Week 17: ‚ñ†
Phase 2C: Interest Engine | Week 18: ‚ñ†; Week 19: ‚ñ†
Phase 2C: Product Configuration | Week 18: ‚ñ†; Week 19: ‚ñ†
Phase 2C: Regular Savings | Week 19: ‚ñ†; Week 20: ‚ñ†
Phase 2C: High-Yield Savings | Week 20: ‚ñ†; Week 21: ‚ñ†
Phase 2C: Goal Savings | Week 20: ‚ñ†; Week 21: ‚ñ†
Phase 2C: Locked Savings | Week 21: ‚ñ†; Week 22: ‚ñ†
Phase 2C: Savings APIs | Week 18: ‚ñ†; Week 19: ‚ñ†
Phase 2C: Savings Testing | Week 22: ‚ñ†
Phase 2C: Savings Analytics | Week 22: ‚ñ†; Week 23: ‚ñ†
Phase 2D: Loan Data Model | Week 21: ‚ñ†
Phase 2D: Credit Bureau | Week 23: ‚ñ†; Week 24: ‚ñ†; Week 25: ‚ñ†
Phase 2D: AI Credit Scoring | Week 23: ‚ñ†; Week 24: ‚ñ†; Week 25: ‚ñ†
Phase 2D: Approval Workflow | Week 22: ‚ñ†; Week 23: ‚ñ†
Phase 2D: Repayment Engine | Week 24: ‚ñ†; Week 25: ‚ñ†
Phase 2D: Personal Loan Screen | Week 24: ‚ñ†; Week 25: ‚ñ†
Phase 2D: Business Loan Screen | Week 25: ‚ñ†; Week 26: ‚ñ†
Phase 2D: Quick Loan Screen | Week 25: ‚ñ†; Week 26: ‚ñ†
Phase 2D: Loan APIs | Week 23: ‚ñ†; Week 24: ‚ñ†
Phase 2D: Loan Testing | Week 26: ‚ñ†
Phase 2D: Loan Analytics | Week 26: ‚ñ†; Week 27: ‚ñ†
Phase 3A: Bulk Transfer Data | Week 23: ‚ñ†
Phase 3A: Transfer Templates | Week 23: ‚ñ†; Week 24: ‚ñ†
Phase 3A: Scheduled Transfers | Week 24: ‚ñ†; Week 25: ‚ñ†
Phase 3A: Bulk Transfer Screen | Week 25: ‚ñ†; Week 26: ‚ñ†
Phase 3A: Templates Screen | Week 25: ‚ñ†; Week 26: ‚ñ†
Phase 3A: Transfer Testing | Week 26: ‚ñ†
Phase 3B: Multi-Account Data | Week 24: ‚ñ†
Phase 3B: Joint Account | Week 25: ‚ñ†; Week 26: ‚ñ†
Phase 3B: Account Switching | Week 26: ‚ñ†; Week 27: ‚ñ†
Phase 3B: Multi-Account Screen | Week 26: ‚ñ†; Week 27: ‚ñ†
Phase 3B: KYC Enhancement | Week 24: ‚ñ†; Week 25: ‚ñ†; Week 26: ‚ñ†
Phase 3C: Biller Integration | Week 27: ‚ñ†; Week 28: ‚ñ†; Week 29: ‚ñ†
Phase 3C: Bill Categories | Week 27: ‚ñ†
Phase 3C: Recurring Bills | Week 28: ‚ñ†; Week 29: ‚ñ†
Phase 3C: Bill Payments Screen | Week 28: ‚ñ†; Week 29: ‚ñ†
Phase 3C: Bill History | Week 29: ‚ñ†
Phase 3D: Save-as-You-Transact | Week 27: ‚ñ†; Week 28: ‚ñ†
Phase 3D: Auto-Save Screen | Week 28: ‚ñ†; Week 29: ‚ñ†
Phase 3D: Reporting Engine | Week 28: ‚ñ†; Week 29: ‚ñ†; Week 30: ‚ñ†
Phase 3D: Report Builder | Week 29: ‚ñ†; Week 30: ‚ñ†
Phase 3D: Support Integration | Week 30: ‚ñ†; Week 31: ‚ñ†
Security: 2FA/MFA | Week 20: ‚ñ†; Week 21: ‚ñ†; Week 22: ‚ñ†
Security: Enhanced Biometric | Week 22: ‚ñ†; Week 23: ‚ñ†
Security: HSM Integration | Week 23: ‚ñ†; Week 24: ‚ñ†; Week 25: ‚ñ†; Week 26: ‚ñ†
Security: WAF Protection | Week 24: ‚ñ†; Week 25: ‚ñ†; Week 26: ‚ñ†
Security: Fraud Detection | Week 25: ‚ñ†; Week 26: ‚ñ†; Week 27: ‚ñ†; Week 28: ‚ñ†
Security: Penetration Testing | Week 28: ‚ñ†; Week 29: ‚ñ†
Security: Monitoring Dashboard | Week 26: ‚ñ†; Week 27: ‚ñ†
Integration: Paystack | Week 29: ‚ñ†; Week 30: ‚ñ†; Week 31: ‚ñ†
Integration: Investment Platforms | Week 30: ‚ñ†; Week 31: ‚ñ†; Week 32: ‚ñ†; Week 33: ‚ñ†
Integration: Insurance APIs | Week 31: ‚ñ†; Week 32: ‚ñ†; Week 33: ‚ñ†; Week 34: ‚ñ†
Optimization: Performance | Week 26: ‚ñ†; Week 27: ‚ñ†; Week 28: ‚ñ†
Optimization: Mobile | Week 29: ‚ñ†; Week 30: ‚ñ†
Optimization: Caching | Week 27: ‚ñ†; Week 28: ‚ñ†
Optimization: Load Testing | Week 29: ‚ñ†; Week 30: ‚ñ†
Optimization: CDN | Week 30: ‚ñ†
Documentation: API Docs | Week 28: ‚ñ†; Week 29: ‚ñ†
Documentation: User Guides | Week 30: ‚ñ†; Week 31: ‚ñ†; Week 32: ‚ñ†
Documentation: Admin Guides | Week 29: ‚ñ†; Week 30: ‚ñ†
Documentation: Onboarding Docs | Week 30: ‚ñ†; Week 31: ‚ñ†
MILESTONE MARKERS
Platform Admin Complete | Week 16: ‚ñ†
Transaction Reversals Live | Week 20: ‚ñ†
NIBSS Production Integration | Week 23: ‚ñ†
Savings Products Live | Week 23: ‚ñ†
Loan Products Live | Week 27: ‚ñ†
Enhanced Transfers Complete | Week 26: ‚ñ†
Bill Payments Live | Week 29: ‚ñ†
Security Hardening Complete | Week 29: ‚ñ†
Performance Optimization | Week 30: ‚ñ†
Full Platform Launch | Week 34: ‚ñ†
CRITICAL PATH INDICATOR
Critical Path | [10 empty] | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ† | ‚ñ†
LEGEND
‚ñ† = Task in progress/planned
Blank = No activity
Critical Path = Backend + Frontend dependent tasks that determine minimum project duration